## Sheet1
Exercise 4: Implementation Goals and Milestones
After completing Exercise 4, a district will have organized the work of implementing NGSS into categories, and articulated goals and milestones for each.
Identify Categories |  | Choose Goals | Draft Milestones | Determine Dependencies | Assign Roles | Deadline | Work through the following six steps, using the table provided to articulate the major categories of work, goals for each, and the milestones to check in on progress.
1 | [6 empty] | Identify categories. Identify categories or initiatives of the district’s education system that will require changes for successful implementation of NGSS. Categories might include equity and access, management, professional learning, instructional materials, communications, collaboration, school structures, and student outcomes. Refer to the National Research Council’s Guide to Implementing the Next Generation Science Standards for more information.
2 | [6 empty] | Choose goals. Each category needs a definition of success—a statement or measure that describes what the district is seeking, and a way to determine when success has been reached. There are many examples of goals in the NGSS District Implementation Indicators document.
3 | [6 empty] | Draft milestones. After identifying the major categories of implementation, identify several milestones within each category. Each milestone should describe a tangible accomplishment that represents progress, and milestones should be distributed over time so that the overall work can be regularly monitored.
4 | [6 empty] | Determine dependencies. Look at the categories and their milestones identified and determine whether certain categories depend on others. What categories need to be set in motion first? Do these categories need to be completed before others can begin to move? Adjust goals and milestones as appropriate.
5 | [6 empty] | Assign roles. Think about who needs to be involved in planning and managing each category. From the district leadership team, who will be managing each category, and will that individual need a support team to achieve certain milestones? What protocols are needed to ensure effective communication within and across teams for each category?
Identify target completion date. After filling out the first five columns of the following chart, look at the major milestones that need to be accomplished and consider what steps the district must take to reach those goals. With these steps in mind, consider target completion dates so that implementation leaders can start to lay out a path and a timeline for each category and its milestones.